11 & 15
Post final builds/installers/manual zip to SourceForge ().

Then set the default download for each platform. For each, click on the 'i' button for the file, then check the appropriate checkbox(es) in the "Default Download For:" section. This means that on the SourceForge Audacity project page, the big green download button offers the Windows installer, on Mac the DMG, and on Linux, BSD, and Solaris the minsrc tarball.
post finals
finish
16.2
assignee
RM:
   1. Discusses freeze dates. There are 2 dates, that start the freeze phases:

       1.1. GUI freeze (should typically be 5-7 days) – Nothing in the GUI is allowed to change, so the Manual can be completed.

       1.2. code/manual freeze: Everything is frozen, for production of Release Candidates.

   2. Fills in agreed tasks to complete, specific to this release, and puts them into steps 4.*. This includes reviewing and deciding on “patch_ready” and P1 (maybe P2) Bugzilla entries.

   3. Gets commitments (“assignees” column) for all tasks below.
Update audacity.pot with the frozen strings, and post to audacity.sourceforge.net. Batch update the .po files with the updated messages from the .pot file.
See

Announce to audacity-translation when this is completed.
Increment the version number in mac/compile.txt. (We keep it at the previous version during alpha period, because it's linked to, online.)
Gale
16.1
Post final builds/installers (including manual.zip) to current download host(s).
   1. Delete the RCs including the manual (don't forget deprecated ones) to avoid user confusion and to conserve space.
   2. Set all the previous version files to "Deprecated".
   3. Set all the new version files to "Featured".
8.1
manual
Bump the version number on the front page of Manual.
See http://manual.audacityteam.org/index.php?title=Main_Page
6.1
GUI
freeze
dev
In Audacity.h, set IS_ALPHA to 0.
5
6.2
GUI
freeze
dev
Increment the version number in win/compile.txt. (We keep it at the previous version during alpha period, because it's linked to, online.)
5
Increment the version number in mac/compile.txt. (We keep it at the previous version during alpha period, because it's linked to, online. ***TODO: Why not link to the older copy instead?***)
6.3
GUI
freeze
dev
5
6.4
6.1
7
6
7.1
7.2
6.1
5
6.*
6.2
Prepare and commit README.txt.
doc
6.4
GUI
freeze
5
6.3
## Sheet1
step	phase	category	task	depends / on step(s)	assignee(s)	status	target / date	completion / date	result
1	planning	discuss	Tech Leaders designate and announce Release Manager (RM).	n/a	TL's				<who is RM>
2	planning	discuss	RM: / 2.1. Discusses freeze dates. There are 2 dates, that start the freeze phases: / 2.1.1. GUI freeze (should typically be 5-7 days) – Nothing in the GUI is allowed to change, so the manual and translations can be completed. / 2.1.2. After the manual is completed, code/manual/translations freeze: Everything is frozen, for production of Release Candidates. / 2.2. Fills in agreed tasks to complete, specific to this release, and puts them into steps 4.*. This includes reviewing and deciding on “patch_ready” and P1 (maybe P2) Bugzilla entries. / 2.3. Gets commitments (“assignees” column) for all tasks below.	1	RM
3	planning	announce	RM sets and announces agreed release-specific tasks, planned string/GUI freeze, and code/manual freeze dates/times.	2	RM
4.*	dev/QA/doc	release- / specific	<This section is to be filled in for each specific release, one 4.* line for each task agreed to be in the release.>	2	RM
5.1	GUI / freeze	announce	At the designated date/time, RM announces start of GUI freeze phase.	3 & 4	RM
5.2	GUI / freeze	announce	Update audacity.pot with the frozen strings, and post to audacity.sourceforge.net. Batch update the .po files with the updated messages from the .pot file. / See http://wiki.audacityteam.org/wiki/Translating_Audacity#Updating_existing_translations / Announce to audacity-translation when this is done, so translations can be completed.	5.1	<?>
6.1	GUI / freeze	doc	Prepare and commit README.txt.	5
6.2	GUI / freeze	translations	Code-string translators submit translations based on frozen strings.	5	(translators)
6.3	GUI / freeze	manual	Make all other necessary updates to Manual for this version.	5
7.1	GUI / freeze	dev	In Audacity.h, set IS_ALPHA to 0.	6
7.2	GUI / freeze	dev	Increment the version number in win/compile.txt. (We keep it at the previous version during alpha period, because it's linked to, online.)	5
7.3	GUI / freeze	dev	Increment the version number in mac/compile.txt. (We keep it at the previous version during alpha period, because it's linked to, online. ***TODO: Why not link to the older copy instead?***)	5
8.2	GUI / freeze	manual	Make all other necessary updates to Manual for this version.	5
9	code/manual / freeze	release / candidates	RM announces start of code/manual freeze phase. Release Candidates (RC's) iterative cycle(s) begins. / Our policy is to ship no Modules (e.g., mod-nyq-bench), so for Windows and Mac, RC builders should make sure no Module is included in any RC.	6, 7, & 8	RM
10.1	code/manual / freeze	release / candidates	Create the Local Manual. See http://wiki.audacityteam.org/wiki/Create_Local_Manual.	9
10.2	code/manual / freeze	release / candidates	Build and post Windows installer (includes Manual). / See http://wiki.audacityteam.org/wiki/Release_Process/Win	9
10.3	code/manual / freeze	release / candidates	Build and post Windows .zip (no Manual). / See http://wiki.audacityteam.org/wiki/Release_Process/Win#Create_the_zip_version	9
10.4	code/manual / freeze	release / candidates	Build and post Mac .dmg (includes Manual). / See http://wiki.audacityteam.org/wiki/Release_Process/Mac	9
10.5	code/manual / freeze	release / candidates	Build and post Mac .zip (no Manual). / See http://wiki.audacityteam.org/wiki/Release_Process/Mac	9
10.6	code/manual / freeze	release / candidates	Create and post Linux minimal source tarball. / See http://wiki.audacityteam.org/wiki/Building_Release_Tarballs	9
11	code/manual / freeze	test	RM announces start of new RC 48-hour testing cycles. Testing takes place for 48 hours, iteratively, until we achieve an RC that we agree is final. If an RC fails, we fix the problems, then go back to step 10. When all RC's of next set are posted, deprecate the previous posts. / * Test installers and zips, including over existing install. / * Test on non-developer machines, for runtime issues.	10	RM, / RC-testers
12.1	code/manual / freeze	release / announcements	website changes: new release news item (htdocs/include/news.inc.php), summarizing most important points from the committed README.txt	5
12.2	code/manual / freeze	release / announcements	website changes: htdocs/latest/versions.inc.php / version numbers and file sizes	5
12.3	code/manual / freeze	release / announcements	website changes / * http://audacity.sourceforge.net/about/ / * http://audacity.sourceforge.net/about/features	5
13.1	code/manual / freeze	release / announcements	wiki release notes: new wiki release notes page, e.g., http://wiki.audacityteam.org/wiki/Release_Notes_2.0.4	5
13.2	code/manual / freeze	release / announcements	wiki release notes: Copy the new "Changes in version" text from README.txt into new wiki release notes.	12.3
14	code/manual / freeze	release / announcements	Do the wiki Release Announcement, per http://wiki.audacityteam.org/wiki/Release_Process/Release_Announcements.	13.2
15	code/manual / freeze	release / announcements	Clear the text on http://wiki.audacityteam.org/wiki/Known_Issues.	14	n/a
16	finish	post finals	Post final builds/installers (including manual.zip) to current download host(s). / 1. Delete or rename the RCs including the manual (including deprecated ones) to avoid user confusion and to conserve space. / 2. Set all the previous version files to "Deprecated". / 3. Set all the new version files to "Featured".	11 & 15
17	finish	post finals	Upload Manual from which the final manual.zip was created to manual.audacityteam.org to provide online version. The internal structure of Manual is complex, but currently best option for future releases is to open the dumped manual at audacity-src/help/manual, copy the four folders (images, m, man, manual) and three files (quick_help.html, index.html, favicon.ico) to the "htdocs/o" directory on the server.	11 & 15
18.1	finish	release / announcements	Commit the website changes to SVN and push to the website (http://wiki.audacityteam.org/wiki/Editing_audacity.sourceforge.net#Updating_the_web_server_from_SVN) so that it goes into the audacity_website.pot file and is then available to website translators.	16 & 17
18.2	finish	release / announcements	Make the Forum announcement.	16 & 17
18.3	finish	release / announcements	Announce the release to audacity-* mailing lists.	16 & 17
18.4	finish	release / announcements	Announce the release to SourceForge (https://sourceforge.net/news/?group_id=6235).	16 & 17
18.5	finish	release / announcements	Announce the release to the Dreamhost announce list (http://audacity.sourceforge.net/#announce).	16 & 17
19	finish	tag	Tag the Release: Since 2.0.0, we tag both audacity-src and website at the same time. / * This is the template SVN command to use. It performs a minimal copy server-side instead of copying from your working copy, so runs much more quickly than transfer from working copy: / svn copy -m "Tag release of Audacity 1.3.x" https://audacity.googlecode.com/svn/audacity-src/trunk/ https://audacity.googlecode.com/svn/audacity-src/tags/Audacity_1_3_x / * For TortoiseSVN, in the Branch/Tag dialog, use the HEAD radio button option to get this server-side copy.	18
20	finish	wrap-up	Lift code/translations/manual freezes.	19	RM
21.1	finish	move on	In src/Audacity.h, set IS_ALPHA to 1.	20
21.2	finish	move on	Increment the version number in src/Audacity.h.	20
21.3	finish	move on	Review and commit any patch_ready Bugzilla entries that were not included in the release.	20